## Slide 1: Going online through four doors
Kristen A. Lewis
&
Verna J. Edwards

## Slide 2: Problem #1
How can we safely train our faculty and staff during the COVID-19 pandemic?

## Slide 3: Decision
Vandenberg Faculty Development decided to put all our courses online on Blackboard.

## Slide 4: Problem #2
How can we efficiently and effectively deliver our courses online?

## Slide 5: Preliminary Questions and Answers
What do we already have?
BIC on Blackboard – a model
Qualified online instructors
Qualified online designers

## Slide 6: Preliminary questions and answers
What do we need?
Blackboard licenses x 5
Time to train designers
Time to train instructors

## Slide 7: Making it happen
Phase 1
Attained Blackboard licenses
Copied and renamed BIC course shell
Assigned designers to develop online content (4 weeks per course)

## Slide 8: Making it happen
Phase 2
TDE created training aids and trained designers
ITU created training aids and trained instructors
Zoom meetings to decide lesson timing on Blackboard Collaborate

## Slide 9: Making it happen
Phase 3: “Four Doors +”
All content under four buttons (doors):
Activities: includes appraisals
Assessments: includes PCs, quizzes and written tests
Café: includes Discussion Board and collaboration
Library: includes instructional materials, references and resources
+ Collaboration: used for real-time lecture

## Slide 10: Making it happen
Phase 4
Practice with instructors
Lecture on Blackboard Collaborate
Turn in appraisals and PCs on Discussion Board
Set up Collaborate space for teaching

## Slide 11: Making it happen
Phase 5
Deliver courses on Blackboard from home
Assist students and instructors with Blackboard and connectivity issues
Evaluate in real-time and adjust as necessary

## Slide 12: Results
Were our customers satisfied? Did we meet their needs?
5 courses designed and delivered online on Blackboard in 6 months
EOC scores exceptional – higher than with classroom-based delivery
Increased enrollment; much interest in courses
Instructors very satisfied with new delivery method and platform
All staff and faculty training requirements met

## Slide 13: Lessons learned
Keep it simple!
Don’t reinvent the wheel; use what you have
Train designers and instructors
Practice before live delivery
Collaborate, collaborate, collaborate!!!

## Slide 14: Questions???